## Sheet1
|  |  |  | Activities as a result of the Interference Workshop 5th of October in Lille |  |  |  | Status 25/02/13 V06
|  | Status |  | Closed | Action Closed, some items pending | In progress | Delayed
Category | [8 empty] | Delivery date
ST | LT | Status | AP | Activity | Sub activity | Responsibility | Start | Expected result/Deliverables | Expected | Closed | Remarks
|  |  | 1 | Follow-up group
X |  |  | 1.1 |  | Creation | ERA/Com | 2012-11-12 | Definition of content | Feb/2013 | Feb/2013 | First step done, group (4) defined (ERA/DG MOVE/DG CONNECT). Terms of Reference being sent by Commission.
X |  |  | 1.2 |  | Nomination | ERA/Com | Feb/2013 | Inform the participants | Feb/2013 | Feb/2013 | Invitations sent. Nominations have arrived. PENDING: Nomination from ERFA has not been submitted.
X |  |  | 1.3 |  | Dates | ERA/Com | Feb/2013 | Inform the participants | Feb/2013 | Feb/2013 | First meeting 25 Feb. Following: end of May 2013
|  |  | 2 | Creation of tools and rules
X |  |  | 2.1 |  | Discussion with DG Connect to understand functioning of RSC rules | ERA/DG MOVE | 2012-12-05 | RSC to review the situation of GSM-R and draw the way forward | 2013-03-21 |  | RSC#42: Presentation took place. No final decision on the way forward; shifted to the RSC#43 (20-21 March).
X |  |  | 2.2 |  | WG FM (Correspondence Group on GSM-R) | ECC | 2012-10-03 | Analyse the situation of GSM-R and prepare WG FM decision on the way forward | 2013-05-24 |  | GSM-R Correspondence group will finish its activities in a few months.
X |  |  | 2.3 |  | New ECC Report (?) | ECC | Q3 2013 | Study related to possible new tools and rules |  |  | To be decided by WG FM Scope to be defined
|  |  | 3 | Test Campaign
X |  |  | 3.1 |  | Preparation | UIC |  | Confirmation of participants | End of Dec. | Dec.2012 | Planning defined, participants confirmed
X |  |  | 3.2.1 |  | Lab test execution for new modules | UIC |  | Test results - splitted in voice and data if needed | End of 2012 | 2013-01-18 | Test performed from 15 to 18 of Jan/13. Report is being generated. TO BE UPDATED BY UIC.
X |  |  | 3.2.2 |  | Field test execution for filters and new modules | UIC |  | Test results - splitted in voice and data if needed- indicating the real environment conditions | 2nd Q 2013 |  | TO BE UPDATED BY UIC: UIC has informed that the test results for filters are available in the report from ISPRA. Follow-up test campaign to be organized together with CEPT. Discussion on the need of performing field tests to benchmark the different equipments available in the same conditions (real environment). To be discussed by the group(4).
X |  |  | 3.3 |  | Discussion of results | UIC/ERA |  | Risk assessment for the different solutions | 2nd Q 2013 |  | Technical assessment as basis for the CBA
X |  |  | 3.4 |  | Decision | ERA |  | Presentation of the proposal to the CG | End 2013
|  |  | 4 | Cab radio evolution | [6 empty] | EDOR to be included
| x |  | 4.1 |  | New module specification | UIC/Industry |  | Specification |  |  | Final decision by the group (4)
| x |  | 4.2 |  | New module implementation | Industry |  | Implementation plan
| x |  | 4.3 |  | Filter specification | UIC/Industry |  | Specification
| X |  | 4.4 |  | Specification of new front-end and cab radio | UIC/Industry |  | Specification
|  |  | 5 | CCM Process (5)
X |  |  | 5.1 |  | Frequency range reduction for GSM-R voice cab radios | ERA/MS | 2012-11-12 | CR to be created | 1Q 2013 |  | CR created in UIC, to be transferred to ERA. Suggestion: to study data and voice terminals separately, inlcuding their resistence to interferences.
X |  |  | 5.2 |  | Creation of new baseline release | ERA | 1.Q 2013 | Baseline release (GSM-R B0 r4) | 4Q 2013 |  | Including maintenance issues
X |  |  | 5.3 |  | Creation of new EIRENE version | UIC |  | New EIRENE version (FRS 7.4.0/SRS 15.4.0) | 4Q 2013
| X |  | 5.4 |  | Creation of FFIS for new modules (6) | UIC |  | Form-Fit Interface Specification |  |  | Interface definition, to allow the introduction of new modules
X |  |  | 5.5 |  | Update of ANNEX A of TSI (7) | DG Move/ERA | End 2013/2015 | Recommendation to be issued by ERA | 2014 |  | Possible new functions
| X |  | 5.6 |  | Next GSM-R Baseline including new cab radio | ERA |  |  |  |  | tbd
| X |  | 5.7 |  | Next Baseline including future Telecom System for Railways | ERA |  |  |  |  | tbd
|  |  | 6 | Legal activities
X |  |  | 6.1 |  | RSC agenda point on GSM-R | DG Connect |  | GSM-R as an agenda point for RSC | Each RSC | N/A | Chair asks (under AOB) about possible updates from delegations
x |  |  | 6.1.b |  | Interaction with ECC (evaluate the need of a Mandate to CEPT?) | DG Connect/ECC | 2014 | Possible mandate to CEPT/ECC or indirect support to ECC activity on GSM-R |  |  | based on ECC results and i.a. on outcome of RSC#43
X |  |  | 6.2 |  | Legal interpretation of Art. 20 in the Directive 2002/21/EC (Framework) | DG Connect |  | Interpretation of the Legal Service | 1Q 2013 | 2012-10-28 | Legal Service has given an answer : "GSM-R operators and undertakings providing public electronic communications networks [...] seem to operate a private electronic communications network, which is not totally excluded from the scope of the regulatory framework. [...] the national law should grant private operators the possibility to address the NRAs as regards the disputes that arise in relation with obligations provided in the framework".
X |  |  | 6.3 |  | Analysis of the situation after expiration of the GSM licenses | ERA/DG Connect |  |  |  |  | To be discussed by the group (4)
X |  |  | 6.4 |  | Evaluate the possibility of cab radio evolution | DG Connect |  |  |  |  | In paralell to the work of the telecom world.
X |  |  | 6.5 |  | Distribution of Report of RSPG WG on efficient interference management | DG Connect |  | Report distribution |  |  | Draft available. Final on November 2013.
|  |  | 7 | Economical Assessment
| x |  | 7.1 |  | New front-end (study) | ERA | 2Q 2013 | study result
| X |  | 7.2 |  | Next generation of cab radio (study) | ERA | 2Q 2013 | study result
X |  |  | 7.1 |  | CBA for each of the envisaged solutions related to the public network | ERA-EE |  | CBA per Site | End 2013 |  | With the support of the Public Operators
X |  |  | 7.3 |  | Assessment (CBA) for the envisaged solutions related to the GSM-R networks and GSM-R terminals | ERA-EE |  | CBA for the different technical solutions | End 2013 |  | With the support of the railway stakeholders and the GSM-R industry
|  |  | 7.4 |  | CBA for any other technique identified within ECC | ERA-EE |  |  |  |  | With the support of the Public Operators, railway stakeholders and the GSM-R industry
X |  |  | 7.2 |  | CBA analysis for GSM-R outages due to interference | ERA-EE |  | Outage cost per train | End 2013 |  | With the support of the railway stakeholders
|  |  | 8 | Funding
X |  |  | 8.1 |  | Analyse the possibility to get funding for the implementation in the cab (filter, module) and parts of the infrastructure | DG MOVE |  |  | 2Q 2013 |  | Wait for the conclusion of negotiations on CEF
|  |  | 9 | Interference data base
X |  |  | 9.1 |  | Provide accurate data on interference locations reported to the radio regulators. | DG CONNECT/ECC (National Regulatory Authorities) | cont. | Reported interferences overview in Europe | cont. |  | Location, length, nature of the interference (wideband or narrowband, blocking, intermodulation, unwanted emissions) have to be reported in order to retrieve evidences of the issue. Actions taken by the regulators should be collected. Questionnaire sent by CEPT to NRAs.
X |  |  | 9.2 |  | Provide accurate data on locations suffering interferences, coming from the railways stakeholders | UIC | cont. | Existing interferences overview in Europe | cont. |  | Location, length, nature of the interference (wideband or narrowband, blocking, intermodulation, unwanted emissions) have to be reported in order to retrieve evidences of the issue. Also, indication if they have been reported to the NRA.
|  | Explanations |  | Status information:
|  |  |  | In progress |  | Remarks
|  |  |  | Risk under control |  | 1) The activities are only listed, there is no order/dependencies between the main topics
|  |  |  | Critical path |  | 2) After combination/bundling, projects will be created
|  |  |  | Delayed |  | 3) Action points related to the strategy (not mentioned during the workshop) have been included in this list (to be discussed)
|  |  |  | point closed, some items pending |  | 4) GSM-R Follow-Up Group
|  |  |  | Closed |  | 5) CCM= Change Control Management. Process in ERA to manage documents modification
6) FFIS = Form-Fit Interface Specification
7) TSI = Technical Specification of Interoperability, part of Railway EU regulation
|  |  | ST | Short term
|  |  | LT | Long term