|  |  | E |
| --- | --- | --- |

| MARITIME SAFETY COMMITTEE 99th session Agenda item 5 | MSC 99/5/n 08 March 2018 Original: ENGLISH |
| --- | --- |

Regulatory scoping exercise for the use of Maritime Autonomous Surface Ships (MASS)

Plan of approach for the scoping exercise

Submitted by Australia, Canada, Denmark, Estonia, Finland, Japan, the Netherlands, Norway, Singapore, Sweden, the United Kingdom, the United States, IMarEST and IMCA

| SUMMARY |  |
| --- | --- |
| Executive summary: | In order to ensure that an output on "Regulatory scoping exercise for the use of Maritime Autonomous Surface Ships (MASS)" will be completed by the target completion year of 2020, the co-sponsors in this document propose a plan of approach for the scoping exercise. |
| Strategic direction: | 2 (Integrate new and advancing technologies in the regulatory framework) |
| Output: | 2.7 (Regulatory scoping exercise for the use of Maritime Autonomous Surface Ships (MASS) (2020)) |
| Action to be taken: | Paragraph 17 |
| Related documents: | MSC 99/INF.3, MSC 98/20/2, MSC 98/20/13, MSC 98/23 |

- This document is submitted in accordance with paragraph 6.12.4 of MSC-MEPC.1/Circ.5 on Organization and method of work of the Maritime Safety Committee and the Marine Environment Protection Committee and their subsidiary bodies, taking into account resolution A.1111(30) on Application of the Strategic Plan of the Organization.

- It proposes a plan of action for undertaking a regulatory scoping exercise, that will identify the need for amendments and/or additions to the existing regulatory framework in IMO, in order to enable the safe, secure and environmentally sound operation of entirely or partly unmanned Maritime Autonomous Surface Ships (MASS).

Introduction

- The Committee at its 98th meeting considered document MSC 98/20/2 (Denmark, Estonia, Finland, Japan, the Netherlands, Norway, Republic of Korea, the United Kingdom and the United States), proposing to undertake a regulatory scoping exercise to determine how the safe, secure and environmentally sound operation of Maritime Autonomous Surface Ships (MASS) might be introduced under existing IMO instruments, and document MSC 98/20/13 (ITF) which commented on document MSC 98/20/2.

- The Committee, following an in-depth discussion on the proposed new output and the commenting document, expressed its general support for the output on the regulatory scoping exercise, and agreed to include in the 2018-2019 biennial agenda of the Maritime Safety Committee and the provisional agenda for MSC 99, an output on "Regulatory scoping exercise for the use of Maritime Autonomous Surface Ships (MASS)", with a target completion date of 2020.

- This paper proposes a plan of action for undertaking a regulatory scoping exercise, to take place within the existing IMO instruments, that will identify the need for amendments and/or additions to the existing regulatory framework in IMO, in order to enable the safe, secure and environmentally sound operation of entirely or partly unmanned Maritime Autonomous Surface Ships (MASS). The plan of approach will assist discussions and progress on this subject, including the establishment of a working group at this session of the Committee.

Discussion

- Since MSC 98 the co-sponsors have noted that the concept of MASS is developing even faster than envisaged, and therefore it is essential the Organization is proactive on this issue to ensure that the scoping exercise is completed in a timely manner.

- The regulatory scoping exercise addresses a complex issue that may affect the entire Organization.  It will have an impact on many areas of IMO’s remit including safety, security, the ship / shore interface and interactions with ports, pilotage, responses to incidents and the marine environment. The implications and effects that increased automation may have on the human element, both at sea and ashore, will also need consideration.

- Of particular importance is the need to address and describe the various concepts of autonomy, automation, operations, and manning, and how these will impact the applicability of present and future rules and regulations.

- In order to carry out the regulatory scoping exercise a preliminary vocabulary should be developed with a set of descriptions for both MASS and for autonomy for the purposes of the scoping exercise. Furthermore, a consistent approach should be established for analysing the existing relevant IMO instruments. This is necessary to allow for a common understanding and facilitate the scoping process, acknowledging that both the vocabulary and the approach may have to be modified as more knowledge and understanding is developed.

- Any outcome of the proposed scoping exercise should also consider the latest developments and recommendations on maritime cyber risk management.

- To guide the scoping exercise, a detailed work plan should be established with a clearly defined scope of work, clear deadlines and deliverables towards the target completion date of 2020.

Proposed approach

- To ensure that an output on "Regulatory scoping exercise for the use of Maritime Autonomous Surface Ships (MASS)" will be completed by the target completion year of 2020, the co-sponsors propose that the Committee makes arrangements for the establishment of working groups and intersessional correspondence groups to achieve the output by MSC 102. 
The following structure of working and correspondence groups is proposed:

  - MSC 99 – Working Group (2018)

  - Intersessional correspondence group reporting provisionally to MSC 100 and finally to MSC 101

  - MSC 100 – Working Group (2018)

  - Intersessional correspondence group reporting to MSC 101

  - MSC 101 – Working Group (2019)

  - Intersessional correspondence group providing final report to MSC 102

  - MSC 102 – Working Group (2020)

- The working groups, supported by the intersessional correspondence groups, should deliver a final report to MSC 102 taking into account the decisions made by MSC 98 and further discussions at Committee meetings.

- The report should identify the need for amendments and/or additions to the existing regulatory framework in IMO, in order to enable the safe, secure and environmental operation of entirely or partly unmanned Maritime Autonomous Surface Ships (MASS) to take place within the existing IMO instruments, taking into account the role of the human element.

- It is proposed that the final output report should contain at least the following:

  - List of IMO instruments included in the work;

  - a description of MASS and concepts of autonomy, automation, operations and manning;

  - a vocabulary for use in connection with further work on MASS;

  - a description of IMO instruments;

    - that are currently in force, but may preclude the operation of MASS,

    - that would have no application to the operation of MASS, if the ship is unmanned, as they relate to human presence on board,

    - that do not preclude the operation of MASS, in example by establishing equivalences or interpretations, and/or which may contain gaps and/or pose barriers, but may need to be amended in order to ensure safe, secure and environmentally sound MASS operations;

  - recommendations for the future scope of work on MASS at IMO.

- Proposed draft Terms of Reference for the proposed MSC 99 MASS scoping exercise working group are included at Annex 1.

Action requested of the Committee

- The Committee is invited to consider the information provided and establish a working group at this session guided by the draft terms of reference proposed in Annex 1.

Annex 1

Proposal for draft Terms of Reference for MASS working group at MSC 99

Regulatory scoping exercise for the use of Maritime Autonomous Surface Ships (MASS)

- The working group is, taking into account [list of documents] and decisions made in plenary, instructed to:

  - develop a preliminary vocabulary with a set of descriptions for both MASS and the underlying terminology in order to facilitate the scoping process, addressing and describing the various concepts of autonomy, automation, operation and manning;

  - advise on a consistent approach for analysing the existing relevant IMO instruments with regard to gaps and barriers that do not fully accommodate the operation of MASS, as well as existing opportunities already available, using MSC 98/20/2 as basis;

  - discuss and propose the potential contents and format of a final report to MSC 102;

  - prepare a detailed work plan for the scoping exercise with clear deadlines and deliverables to ensure completion of the scoping exercise output item by 2020;

  - consider whether it is necessary to establish a correspondence group and, if so, prepare Terms of Reference for consideration by the Committee; and

  - submit a written report to the committee by Thursday, 24 May 2018.

Noting the limited time between MSC 99 and MSC 100 it is suggested that MSC 99 establish the Correspondence Group with Terms of Reference that allow it to work through to MSC 101, while providing MSC 100 with a status report. Based upon the progress of the work in the proposed working groups at MSC 99 and MSC 100 respectively, the Committee may decide to change this into two separate correspondence groups. A separate Correspondence Group would be established to work between MSC 101 and 102.